## Resources
Resources Name | Resource Code
Aman Ray | R1
Ashutosh Sahu | R2
Bhavesh Mayekar | R3
Lal Singh Dhaila | R4
Roman Shaikh | R5
Udita Retharekar | R6

## Pair Planning
Week # | Pair 1 | Pair 2 | Pair 3 | Task # | Sprint
Week 1 | Planning |  |  | TBD
Week 2 |  |  |  | TBD
Week 3 |  |  |  | TBD
Week 4 | R1, R2 | R3, R4 | R5, R6 | TBD
Week 5 | R1, R3 | R2, R5 | R4, R6 | TBD
Week 6 | R1, R4 | R2, R6 | R3, R5 | TBD
Week 7 | R1, R5 | R2, R4 | R3, R6 | TBD
Week 8 | R1, R6 | R2, R3 | R4, R5 | TBD
Week 9 | R1, R2 | R3, R4 | R5, R6 | TBD
Week 10 | R1, R3 | R2, R5 | R4, R6 | TBD
Week 11 | R1, R4 | R2, R6 | R3, R5 | TBD
Week 12 | R1, R5 | R2, R4 | R3, R6 | TBD

## Estimate
Issue Id | Summary | Estimation | Estimation presentation | Group Name | Sprint Total
SCM-1 | Use Cases | 2 | 2 | Sprint 1 | 5
SCM-2 | Datasets | 3 | 3 | Sprint 1
SCM-7 | Functional Architecture | 2 | 2 | Sprint 2 | 5
SCM-8 | Technical Architecture | 2 | 2 | Sprint 2
SCM-6 | Pair Programming Plan | 1 | 1 | Sprint 2
SCM-10 | Design and Plan Documents | 2 | 2 | Sprint 3 | 5
SCM-9 | PoC | 3 | 3 | Sprint 3
SCM-12 | Create test cases | 3 | 3 | Sprint 4 | 5
SCM-11 | Create Django Framework | 2 | 2 | Sprint 4
SCM-14 | Populate real time data in database tables | 2 | 2 | Sprint 5 | 5
SCM-13 | Database Design | 3 | 3 | Sprint 5
SCM-16 | Home page skeleton | 3 | 3 | Sprint 6 | 5
SCM-15 | Login | 2 | 2 | Sprint 6
SCM-17 | Home page | 5 | 5 | Sprint 7 | 5
SCM-18 | Individual dashboards | 5 | 5 | Sprint 8 | 5
SCM-19 | Recommendations | 5 | 5 | Sprint 9 | 5
SCM-21 | Integration testing | 3 | 3 | Sprint 10 | 5
SCM-20 | Refactoring | 2 | 2 | Sprint 10
SCM-23 | Documentation | 2 | 2 | Sprint 11 | 5
SCM-22 | Integration testing | 3 | 3 | Sprint 11
SCM-24 | Final Submission | 5 | 5 | Sprint 12 | 5
|  |  |  | Total | 60
Total = 12 weeks X 5 days per week